## 📋 Latest Tracker
Task ID | Phase | Activity | Steps | Planned Start | Planned End | Act. Start | Act. End | Assigned To | Tested By | Testing Status | Status | Progress % | Comments
1 | Project Initiation | Kick Off | Project Kickoff | 2026-07-28 | 2026-07-28 | 2026-07-28 | 2026-07-28 | Robinson |  |  | Completed | 100%
2 | Requirement Gathering | Workshop | Requirement Gathering Workshop — facilitation, business process walkthroughs & minutes | 2026-08-03 | 2026-08-07 | 2026-08-03 | 2026-08-07 | Robinson |  |  | Completed | 100%
3 | Requirement Gathering | Workshop | Requirement Gathering Workshop — SAP integration requirements (reference data, MIRO/FB60) | 2026-08-03 | 2026-08-07 | 2026-08-03 | 2026-08-07 | Anas |  |  | Completed | 100%
4 | Requirement Gathering | Workshop | Requirement Gathering Workshop — IT, infrastructure & architecture requirements | 2026-08-03 | 2026-08-07 | 2026-08-03 | 2026-08-07 | Pranay |  |  | Completed | 100%
5 | Requirement Gathering | BPD Creation | Business Requirement Document (BRD) Creation | 2026-08-11 | 2026-08-12 | 2026-08-11 | 2026-08-19 | Robinson |  |  | Completed | 100%
6 | Requirement Gathering | BPD Sign Off | Business Requirement Document (BRD) Review & Sign-Off | 2026-08-13 | 2026-08-13 | 2026-08-20 | 2026-09-04 | Robinson |  |  | Completed | 100%
7 | UI/UX | UI UX Creation | UI/UX Design | 2026-08-14 | 2026-08-19 | 2026-08-17 | 2026-08-25 | Suganth |  |  | Completed | 100%
8 | UI/UX | UI UX Sign Off | UI/UX Review & Sign-Off | 2026-08-20 | 2026-08-21 | 2026-08-26 | — | Suganth |  |  | Completed | 100%
9 | Env. Setup | Azure Infrastructure | Provisioning of Infrastructure | 2026-09-17 | 2026-09-17 | 2026-08-10 | — | Pranay |  |  | In Progress | 90%
10 | DevOps | Enviornment Setup | Environment Setup, Git/SonarQube, Manual Deployment, SAP/RPA Connectivity | 2026-09-21 | 2026-09-23 | — | — | Pranay |  |  | Not Started | —
11 | Solution Design | Solution Arch Creation | Solution Design & Architecture — HLD, LLD (Database and schema setup) | 2026-08-14 | 2026-08-18 | 2026-08-20 | — | Pranay |  |  | Completed | 100%
12 | Solution Design | Solution Arch Sign Off | Solution Design & Architecture — Review & Sign-Off | 2026-09-18 | 2026-09-18 | 2026-08-26 | — | Pranay |  |  | In Progress | 90%
P1 | PHASE 1 | Core Platform & Standard Invoice Processing | Dev complete 30-Oct-2026 ¦ Functional tests 19–28 Oct (progressive) ¦ Phase 1 E2E 02–03 Nov ¦ SAP integration, ingestion, AI extraction, validation/reconciliation, approvals, notifications. | 2026-09-07 | 2026-11-03 | 2026-08-26 | — | Team |  |  | In Progress | 21%
13 | Phase 1 | Core Application & Foundation | React, Node.js/TypeScript & PostgreSQL application foundation | 2026-08-31 | 2026-08-31 | 2026-08-31 | 2026-08-31 | Rahul |  |  | Completed | 100%
14 | Phase 1 | DevOps & Environment | Environment configuration — Azure resources, networking, Key Vault & deployment pipeline | 2026-09-24 | 2026-09-28 | — | — | Pranay |  |  | Not Started | 0%
15 | Phase 1 | DevOps & Environment | Environment configuration — application settings, environment variables, DB migration & deployment validation | 2026-09-23 | 2026-09-24 | — | — | Rahul |  |  | Not Started | 0%
16 | Phase 1 | DevOps & Environment | Microsoft Entra ID SSO POC and Fiori / Direct Portal entry | 2026-08-26 | 2026-08-31 | 2026-08-24 | 2026-08-26 | Rahul | Suganth | Passed | Dev Complete | 100% | [QA 23-Sep-26 Suganth] Entra SSO login to portal works; unauthenticated API calls return 401.
17 | Phase 1 | Authentication & Access | RBAC, role mapping, authorization and controlled user/role administration | 2026-09-07 | 2026-09-10 | 2026-08-26 | 2026-08-27 | Rahul | Suganth | Passed | Dev Complete | 100% | [QA 23-Sep-26 Suganth] all APIs reject calls without session (401); role resolved from USERS table. Gaps: FE routes not role-gated (sidebar only); /ap-invoice-ocr/extract also allows VENDOR/FINANCE/BUSINESS roles.
18 | Phase 1 | Authentication & Access | Entra ID SSO integration, session validation and logout management | 2026-09-07 | 2026-09-10 | 2026-08-27 | 2026-08-28 | Rahul | Suganth | Failed | Dev Complete | 100% | [QA 23-Sep-26 Suganth] express-session uses in-memory store - every backend restart logs all users out; not safe for multiple instances. Use a Postgres/Redis session store.
19 | Phase 1 | Authentication & Access | Direct Portal Entry with SAP SSO | 2026-09-07 | 2026-09-10 | 2026-08-24 | 2026-08-26 | Rahul | Suganth | Blocked | Dev Complete | 100% | [QA 23-Sep-26 Suganth] SAP IAS SSO disabled in local build - Direct Portal Entry with SAP SSO could not be tested.
20 | Phase 1 | Authentication & Access | Session & Logout Management [RBAC] | 2026-09-07 | 2026-09-10 | 2026-08-31 | 2026-09-01 | Rahul | Suganth | Failed | Dev Complete | 100% | [QA 23-Sep-26 Suganth] sessions lost on every backend restart (in-memory store). Login/logout itself works.
21 | Phase 1 | Admin & Configuration | Invoice category/subcategory and document matrix configuration | 2026-09-07 | 2026-09-10 | 2026-08-17 | 2026-08-19 | Sabrina | Suganth | Passed | Dev Complete | 100% | [QA 23-Sep-26 Suganth] add/remove document type for Manpower persists. Gaps: Invoice Category tab is read-only (no add category/subcategory in UI); all Manpower documents set to Optional for extraction.
22 | Phase 1 | Admin & Configuration | Field/schema and category/document prompt configuration | 2026-09-11 | 2026-09-14 | 2026-08-12 | 2026-08-19 | Sabrina | Suganth | Passed | Dev Complete | 100% | [QA 23-Sep-26 Suganth] fields-to-capture and extraction/classification prompt previews load per invoice type; 7 docs extracted correctly from synthetic Manpower package.
23 | Phase 1 | Admin & Configuration | Validation rule, tolerance and outcome-code metadata configuration (config model & Admin UI) | 2026-09-17 | 2026-09-17 | 2026-08-19 | 2026-09-11 | Sabrina | Suganth | Passed | Dev Complete | 100% | [QA 23-Sep-26 Suganth] SAP mapping create/edit/delete, duplicate mapping blocked (409), tolerance edit persists, validation rule create/toggle/delete OK. Gaps: no endpoint to create/publish a config version (version dropdown is mock); severity/outcome code not exposed in mapping API.
25 | Phase 1 | Admin & Configuration | SLA & Due-Date Settings and Email template integration | 2026-09-07 | 2026-09-10 | 2026-09-07 | 2026-09-10 | Rahul | Suganth | Failed | Dev Complete | 100% | [QA 23-Sep-26 Suganth] (1) SLA started on weekend: Sat 10:00 + 1 business day = Mon 10:00 (expected Tue 08:00). (2) 4 duplicate DRAFT_INVOICE_CREATION SLA clocks on one invoice, shown 'Breached' with '+4h 49m remaining'. (3) Policies reference email templates tpl-18/tpl-21 that do not exist. (4) Warning window (8h) larger than SLA duration (1h) is accepted.
26 | Phase 1 | Admin & Configuration | Reminder Schedules | 2026-09-09 | 2026-09-11 | 2026-09-09 | 2026-09-11 | Rahul | Suganth | Failed | Dev Complete | 100% | [QA 23-Sep-26 Suganth] SLA_TEST_EMAIL override did not replace role recipient (ap.team@essa.com still emailed); on start-up 105 backlog reminders were sent in one burst.
27 | Phase 1 | Admin & Configuration | Escalation Schedules | 2026-09-09 | 2026-09-11 | 2026-09-09 | 2026-09-11 | Rahul | Suganth | Passed | Dev Complete | 100% | [QA 23-Sep-26 Suganth] escalation config (ESC001) saved with targets/channels/template; policy clone/test/delete lifecycle OK. Note: escalation template tpl-21 missing in this DB.
28 | Phase 1 | Admin & Configuration | Email Templates | 2026-09-02 | 2026-09-04 | 2026-09-02 | 2026-09-04 | Rahul | Suganth | Passed | Dev Complete | 100% | [QA 23-Sep-26 Suganth] email templates list (13), preview, duplicate, update and delete all OK.
29 | Phase 1 | Admin & Configuration | Teams Notification Delivery | 2026-09-14 |  | 2026-09-14 |  | Rahul |  |  | In Progress | 30% | We need Microsoft 365 license to send the Teams notifications from the application, I did some code changes but need the license id to test them.
30 | Phase 1 | Invoice Ingestion | AP mailbox visibility, manual polling, connectivity and controlled checkpointing | 2026-09-07 | 2026-09-11 | 2026-08-25 | 2026-08-27 | Sabrina | Suganth | Passed | Dev Complete | 100% | [QA 23-Sep-26 Suganth] manual 'Poll mailbox' and 3-minute scheduler work. Risk: only the newest 25 inbox messages are scanned per poll with no checkpoint - EAPA mail below the top 25 is never picked up.
31 | Phase 1 | Invoice Ingestion | Email, attachment and invoice/bundle registration | 2026-09-14 | 2026-09-15 | 2026-08-25 | 2026-08-26 | Sabrina | Suganth | Passed | Dev Complete | 100% | [QA 23-Sep-26 Suganth] emailed Manpower invoice (INV 520, 18 MB PDF) and synthetic package (INV 901) registered as ESSA invoices with attachment and inbound-email records.
32 | Phase 1 | Invoice Ingestion | File controls, ZIP handling and one-PDF-one-invoice validation | 2026-09-16 | 2026-09-17 | 2026-08-25 | 2026-08-28 | Sabrina | Suganth | Failed | Dev Complete | 100% | [QA 23-Sep-26 Suganth] portal upload rejects ZIP files entirely (even a ZIP with one PDF) - 'No supported files found'. Corrupt PDF correctly rejected ('Invalid PDF').
33 | Phase 1 | Invoice Ingestion | Email subject parsing, category/PO hints, DOCREQ correlation and duplicate controls | 2026-09-18 | 2026-09-21 | 2026-08-25 | 2026-08-26 | Sabrina | Suganth | Failed | Dev Complete | 100% | [QA 23-Sep-26 Suganth] (1) duplicate invoice-number check disabled in code (apInvoiceDocument.service.ts:1579) - 520/PT.ALE-PAU/12/2025 now registered 5x, 568 18x. (2) Malformed [EAPA] subject (PO without ':') silently skipped - no INVALID_SUBJECT record, vendor not informed. (3) App's own DOCREQ emails are re-ingested as vendor replies (NO_DOCUMENT). DOCREQ subject correlation works.
34 | Phase 1 | Invoice Ingestion | SharePoint watch-folder ingestion | 2026-09-22 | 2026-09-23 | 2026-08-27 | 2026-08-28 | Sabrina | Suganth | Passed | Dev Complete | 100% | [QA 23-Sep-26 Suganth] SharePoint intake simulation processed a valid file name (PO/vendor/invoice parsed). Notes: malformed name rejected with misleading message 'Subject must start with [EAPA]'; PO format needs ':' which SharePoint file names cannot contain.
35 | Phase 1 | Invoice Ingestion | Admin-only manual portal invoice upload | 2026-09-04 | 2026-09-04 | 2026-09-08 | 2026-09-08 | Sabrina | Suganth | Passed | Dev Complete | 100% | [QA 23-Sep-26 Suganth] admin manual upload of synthetic Manpower package - 7 documents extracted, invoice 902 created with correct amounts/dates, SLA started, validation ran (9/12, remaining fails due to mock SES/rate data).
36 | Phase 1 | Invoice Ingestion | Missing-document request case creation, vendor email review/send and DOCREQ correlation | 2026-09-24 | 2026-09-28 | 2026-08-25 | 2026-09-09 | Sabrina | Suganth | Failed | Dev Complete | 100% | [QA 23-Sep-26 Suganth] DOCREQ auto-created for exactly the missing docs (REQ-0000028) and emailed; cancel works. BUT email is sent from avensys.dev@outlook.com with no Reply-To, so vendor replies go to the wrong mailbox. Server-side GET validate also raised a false DOCREQ (REQ-0000027).
37 | Phase 1 | Vendor Communication | Vendor response correlation, replacement lineage and controlled reprocessing | 2026-09-29 | 2026-09-30 | 2026-08-25 | 2026-08-26 | Sabrina | Suganth | Failed | Dev Complete | 100% | [QA 23-Sep-26 Suganth] vendor reply correlated to REQ-0000028 and merged (FULFILLED, 3 docs RECEIVED), but auto re-validation after merge set the invoice to draft with 12/12 checks failed. First reply PDF (Faktur/Attendance/PO only) was classified as 'unclassified'.
38 | Phase 1 | Vendor Communication | Invoice/supporting-document storage, metadata/version lineage and secure document access | 2026-10-01 | 2026-10-05 | 2026-08-27 | 2026-08-28 | Sabrina | Suganth | Passed | Dev Complete | 100% | [QA 23-Sep-26 Suganth] section PDFs stored per upload and served only with an authenticated session; supporting documents linked to the invoice.
39 | Phase 1 | SAP Integration | SAP Data intake from EAPA DB | 2026-09-21 | 2026-10-12 | — | — | Anas |  |  | Not Started | 0%
40 | Phase 1 | SAP Integration | PO, Vendor, SES and Negative Vendor lise, GRN and related data export to CSV | 2026-10-05 | 2026-10-12 | — | — | Anas |  |  | Not Started | 0%
41 | Phase 1 | SAP Integration | Exported CSV by ABAP copy to Azure Blob (PO, vendor master, SES, etc.) | 2026-10-05 | 2026-10-12 | — | — | Anas |  |  | Not Started | 0%
42 | Phase 1 | SAP Parking / RPA | PAD/RPA pickup, claim, locking & retry orchestration | 2026-09-16 | 2026-09-28 | — | — | Natheera |  |  | Not Started | 0%
43 | Phase 1 | SAP Parking / RPA | MIRO, FB60 and GOS parking/attachment automation | 2026-09-16 | 2026-09-28 | — | — | Natheera |  |  | Not Started | 0%
44 | Phase 1 | SAP Parking / RPA | SAP result writeback, lifecycle update, failed-item recovery and daily GRN/SES re-match | 2026-09-16 | 2026-09-28 | — | — | Natheera |  |  | Not Started | 0%
45 | Phase 1 | Invoice Orchestration | Create the invoice, invoice document and status history tables in the EAPA PostgreSQL database. | 2026-09-16 | 2026-09-16 | 2026-09-16 | 2026-09-16 | Rahul | Suganth | Failed | Dev Complete | 100% | [QA 23-Sep-26 Suganth] ESSA_INVOICE.CreatedDt stored ~11h behind actual time (timezone offset applied twice) - affects SLA start, dates and filters.
46 | Phase 1 | Invoice Orchestration | Save each ingested invoice to the invoice table, with a duplicate check. | 2026-09-16 | 2026-09-17 | 2026-09-16 | 2026-09-17 | Rahul, Sabrina | Suganth | Failed | Dev Complete | 100% | [QA 23-Sep-26 Suganth] duplicate check disabled - same invoice number saved repeatedly (520 x5, 568 x18).
47 | Phase 1 | Invoice Orchestration | Update the invoice status and save each change to the status history table. | 2026-09-16 | 2026-09-17 | 2026-09-16 | 2026-09-17 | Rahul, Sabrina | Suganth | Failed | Dev Complete | 100% | [QA 23-Sep-26 Suganth] new email invoice (901, incomplete package) set to 'validated' before any validation ran; after DOCREQ merge the status moved back to 'draft'.
48 | Phase 1 | Invoice Orchestration | Create an API to get invoice details, and write unit tests. | 2026-09-30 | 2026-09-30 | — | — | Rahul |  |  | Not Started | 0%
49 | Phase 1 | Invoice Orchestration | Check the PO number exists in the SAP PO tables, mark the invoice as PO or Non-PO, find its category, and save to the invoice table. | 2026-09-28 | 2026-09-29 | 2026-08-12 | — | Sabrina |  |  | In Progress | 50% | Will need SAP data as well as instructions on how to categorise each PO/non-PO invoice.
50 | Phase 1 | Invoice Orchestration | Once the invoice saved, trigger the validation from admin config. (orchastration) | 2026-09-30 | 2026-10-01 | — | — | Sabrina |  |  | Not Started | 0%
51 | Phase 1 | AI Extraction Engine | Azure OpenAI secure connectivity and dynamic prompt / structured schema generation | 2026-09-18 | 2026-09-18 | 2026-08-12 | — | Sabrina |  |  | In Progress | 80% | Azure OpenAI is not available for us to connect with at the moment. We are using our own OpenAI account for now.
52 | Phase 1 | AI Extraction Engine | Document extraction | 2026-09-21 | 2026-09-24 | 2026-09-16 | — | Sabrina |  |  | In Progress | 20%
53 | Phase 1 | Audit trail | Audit trail | 2026-09-25 | 2026-09-25 | 2026-09-10 | 2026-09-16 | Sabrina | Suganth | Passed | Dev Complete | 100% | Completed for login and invoice processing. [QA 23-Sep-26 Suganth] audit trail covers login/logout, intake, classify, extract, validate, DOCREQ issued/received; filters work. Gap: admin configuration changes (mappings, rules, SLA, templates) are not audited.
54 | Phase 1 | Validation & Reconciliation | Reusable deterministic rule framework and mandatory/conditional document completeness validation | 2026-10-01 | 2026-10-05 | — | — | Rahul |  |  | Not Started | 0%
55 | Phase 1 | Validation & Reconciliation | PO/GRN/SES matching, financial arithmetic and SES tolerance validation | 2026-10-06 | 2026-10-09 | — | — | Rahul |  |  | Not Started | 0%
56 | Phase 1 | Validation & Reconciliation | Cross-document reconciliation, result aggregation, error catalogue and controlled revalidation | 2026-10-12 | 2026-10-13 | — | — | Rahul |  |  | Not Started | 0%
57 | Phase 1 | Validation & Reconciliation | Material Domestic / Import base reconciliation — business rules across PO, GRN, invoice & shipping references | 2026-10-14 | 2026-10-15 | — | — | Rahul |  |  | Not Started | 0%
58 | Phase 1 | Validation & Reconciliation | Material Invocie - Domestic / Import — extraction/config mapping & test integration | 2026-10-02 | 2026-10-05 | — | — | Sabrina |  |  | Not Started | 0%
59 | Phase 1 | Category Processing – Standard | Travel Non-PO / HCIS / Consultant / Rental / Medical / Telecom / Hotel — non-PO validation & reconciliation patterns (backend) | 2026-10-16 | 2026-10-19 | — | — | Rahul |  |  | Not Started | 0%
60 | Phase 1 | Category Processing – Standard | Travel Non-PO / HCIS / Consultant / Rental / Medical / Telecom / Hotel — extraction/config/UI integration | 2026-10-06 | 2026-10-07 | — | — | Sabrina |  |  | Not Started | 0%
61 | Phase 1 | Vendor Controls | Negative Vendor hard-block and vendor bank/master mismatch controls | 2026-10-07 | 2026-10-08 | — | — | Natheera |  |  | Not Started | 0%
62 | Phase 1 | Exception Management | Exception workbench UI — remarks, correction/resubmission & re-entry screens | 2026-10-08 | 2026-10-13 | — | — | Sabrina |  |  | Not Started | 0%
63 | Phase 1 | Exception Management | Controlled override & re-entry backend controls | 2026-10-20 | 2026-10-22 | — | — | Rahul |  |  | Not Started | 0%
64 | Phase 1 | Approval Workflow | Workflow instance/stage engine, AP review and DoA / WPC routing | 2026-10-23 | 2026-10-28 | — | — | Rahul |  |  | Not Started | 0%
65 | Phase 1 | Approval Workflow | Tax review, Microsoft Teams approve/reject/request-more-info and rejection/resubmission | 2026-10-29 | 2026-10-30 | — | — | Rahul |  |  | Not Started | 0%
66 | Phase 1 | Approval Workflow | SLA rule evaluation, due-date calculation and reminder scheduling | 2026-09-07 | 2026-09-10 | 2026-09-07 | 2026-09-10 | Rahul | Suganth | Failed | Dev Complete | 100% | [QA 23-Sep-26 Suganth] SLA marked BREACHED before due time (INV 902 started 06:35Z, due 07:35Z, breached 06:40Z; INV 520 breached 2 min after start); warning time computed before start time (8h warning on 1h SLA not capped); reminder configured +3 min sent at start time; duplicate SLA clock created for INV 901 after DOCREQ merge; 135 of 136 SLA instances BREACHED.
67 | Phase 1 | Approval Workflow | Escalation/vendor-chase scheduling, email delivery, Teams/in-app delivery and email template configuration | 2026-09-17 | 2026-09-18 | 2026-08-28 | — | Natheera |  |  | In Progress | 5%
68 | Phase 1 | User Interface / Dashboard | Invoice search, filters, invoice detail and end-to-end transaction timeline | 2026-08-28 | 2026-08-28 | 2026-08-28 | — | Khalid | Suganth | Passed | Dev Complete | 90% | [QA 23-Sep-26 Suganth] invoice list search, vendor/PO type/category/stage filters, paging and detail page work. Note: FE calls missing APIs (/essa/invoices/me/my-work, /essa/dashboard, /essa/pos return 404).
69 | Phase 1 | HITL Review | Build HITL review screen with side-by-side document preview and group queues (Material/Service/Site) | 2026-09-17 | 2026-09-21 | — | — | Sabrina | Suganth | Passed | Dev Complete | 100% | [QA 23-Sep-26 Suganth] HITL screen - side-by-side preview, document tabs, 12-point checklist, edit. Defects to fix: server GET validate fails all rules while UI POST shows 10/12; SES lookup sends inverted period; Berita Acara MH read as 8.1 vs 8,370 (real INV 520 PDF).
70 | Phase 1 | HITL Review | Build HITL 10% sampling rule for straight-through PO invoices and mandatory review for Non-PO | 2026-09-29 | 2026-09-29 | — | — | Pranay |  |  | Not Started | 0%
71 | Phase 1 | Master Data Screens | Build PO master screen (header and line items, open qty/value, status) with search and filter | 2026-09-22 | 2026-09-23 | — | — | Khalid |  |  | Not Started | 0%
72 | Phase 1 | Master Data Screens | Build vendor master screen (code, name, NPWP, PKP status, payment terms, blocked status) with search | 2026-09-24 | 2026-09-24 | — | — | Khalid |  |  | Not Started | 0%
73 | Phase 1 | Master Data Screens | Build vendor bank detail screen with bank change history and mismatch alert log | 2026-09-25 | 2026-09-28 | — | — | Khalid |  |  | Not Started | 0%
74 | Phase 1 | Master Data Screens | Build GRN and SES view screens linked to PO | 2026-09-29 | 2026-09-30 | — | — | Khalid |  |  | Not Started | 0%
75 | Phase 1 | Master Data Screens | Build invoice payment status view (payment doc, date, clearing) | 2026-10-01 | 2026-10-01 | — | — | Khalid |  |  | Not Started | 0%
76 | Phase 1 | Master Data Screens | Build HCIS clearing journal view for Travel Non-PO | 2026-10-02 | 2026-10-02 | — | — | Khalid |  |  | Not Started | 0%
77 | Phase 1 | Master Data Screens | Update the Build SAP data sync status screen (last sync time, record count, failed/quarantined files) | 2026-10-05 | 2026-10-12 | — | — | Anas |  |  | Not Started | 0%
78 | Phase 1 | Vendor Controls | Build negative vendor list screen with manual flag/unflag, reason and history | 2026-10-05 | 2026-10-06 | — | — | Khalid |  |  | Not Started | 0%
79 | Phase 1 | Vendor Controls | Ingest negative listing Excel from Tax Team, auto-flag vendors/invoices and post VAT-on-hold entries All entries would be posted for Invoices, VAT ON-HOLD, to be passed as an indictaor in Invoice posting | 2026-09-16 | 2026-09-28 | — | — | Natheera |  |  | Not Started | 0%
80 | Phase 1 | Vendor Controls | Build vendor enable/disable for AP automation, with history | 2026-10-07 | 2026-10-07 | — | — | Khalid |  |  | Not Started | 0%
81 | Phase 1 | Admin & Configuration | Build configuration draft/approve/publish versioning | 2026-10-14 | 2026-10-16 | — | — | Sabrina |  |  | Not Started | 0%
82 | Phase 1 | Admin & Configuration | Build WHT / tax code matrix screen | 2026-10-08 | 2026-10-09 | — | — | Khalid |  |  | Not Started | 0%
83 | Phase 1 | Admin & Configuration | Build DoA matrix screen | 2026-10-12 | 2026-10-13 | — | — | Khalid |  |  | Not Started | 0%
84 | Phase 1 | Admin & Configuration | Build Internal Order (IO) matrix screen | 2026-10-14 | 2026-10-14 | — | — | Khalid |  |  | Not Started | 0%
85 | Phase 1 | Admin & Configuration | Build prohibited wording list screen | 2026-09-30 | 2026-09-30 | — | — | Pranay |  |  | Not Started | 0%
86 | Phase 1 | Admin & Configuration | Build SAP narration rules screen | 2026-10-01 | 2026-10-01 | — | — | Pranay |  |  | Not Started | 0%
87 | Phase 1 | SAP Integration | Migrate open POs from SAP transaction history | 2026-10-05 | 2026-10-12 | — | — | Anas |  |  | Not Started | 0%
89 | Phase 1 | Admin & Configuration | Configure all 23 invoice categories in Admin (document checklist, fields, prompts, rules) | 2026-10-19 | 2026-10-21 | — | — | Sabrina |  |  | Awaiting ESSA Input | 0%
90 | Phase 1 | DevOps & Environment | Set up CI/CD pipeline for DEV, UAT and PROD | 2026-10-06 | 2026-10-08 | — | — | Pranay |  |  | Not Started | 0%
91 | Phase 1 | Security & API Controls | Confirm and document data privacy (UU PDP) compliance: Azure region, OpenAI no retention, biometric retention | 2026-10-09 | 2026-10-09 | — | — | Pranay |  |  | Not Started | 0%
92 | Phase 1 | Phase 1 Consolidated E2E & Regression | Phase 1 end-to-end regression for all invoice types, with bug fixes and retest | 2026-11-02 | 2026-11-03 | — | — | Team |  |  | Not Started | 0%
93 | Phase 1 | Invoice Type Functional / Scenario Testing | Test Material Domestic invoice flow | 2026-10-19 | 2026-10-19 | — | — | Team |  |  | Not Started | 0%
94 | Phase 1 | Invoice Type Functional / Scenario Testing | Test Material Import invoice flow | 2026-10-19 | 2026-10-19 | — | — | Team |  |  | Not Started | 0%
95 | Phase 1 | Invoice Type Functional / Scenario Testing | Test Rental Equipment invoice flow | 2026-10-20 | 2026-10-20 | — | — | Team |  |  | Not Started | 0%
96 | Phase 1 | Invoice Type Functional / Scenario Testing | Test Subscription invoice flow | 2026-10-20 | 2026-10-20 | — | — | Team |  |  | Not Started | 0%
97 | Phase 1 | Invoice Type Functional / Scenario Testing | Test Travel Non-PO (HCIS clearing) invoice flow | 2026-10-21 | 2026-10-21 | — | — | Team |  |  | Not Started | 0%
98 | Phase 1 | Invoice Type Functional / Scenario Testing | Test Hotel Non-PO invoice flow | 2026-10-21 | 2026-10-21 | — | — | Team |  |  | Not Started | 0%
99 | Phase 1 | Invoice Type Functional / Scenario Testing | Test Import Logistics invoice flow | 2026-10-22 | 2026-10-22 | — | — | Team |  |  | Not Started | 0%
100 | Phase 1 | Invoice Type Functional / Scenario Testing | Test Domestic Logistics invoice flow | 2026-10-22 | 2026-10-22 | — | — | Team |  |  | Not Started | 0%
101 | Phase 1 | Invoice Type Functional / Scenario Testing | Test Consultants (Time Based) invoice flow | 2026-10-23 | 2026-10-23 | — | — | Team |  |  | Not Started | 0%
102 | Phase 1 | Invoice Type Functional / Scenario Testing | Test Consultants (Milestone) invoice flow | 2026-10-23 | 2026-10-23 | — | — | Team |  |  | Not Started | 0%
103 | Phase 1 | Invoice Type Functional / Scenario Testing | Test Medical Services invoice flow | 2026-10-26 | 2026-10-26 | — | — | Team |  |  | Not Started | 0%
104 | Phase 1 | Invoice Type Functional / Scenario Testing | Test Surveillance and Inspection invoice flow | 2026-10-26 | 2026-10-26 | — | — | Team |  |  | Not Started | 0%
105 | Phase 1 | Invoice Type Functional / Scenario Testing | Test Telecom and Internet Services invoice flow | 2026-10-27 | 2026-10-27 | — | — | Team |  |  | Not Started | 0%
106 | Phase 1 | Invoice Type Functional / Scenario Testing | Test CSR / External Relation invoice flow | 2026-10-27 | 2026-10-27 | — | — | Team |  |  | Not Started | 0%
107 | Phase 1 | Invoice Type Functional / Scenario Testing | Test Corporate Credit Card invoice flow | 2026-10-28 | 2026-10-28 | — | — | Team |  |  | Not Started | 0%
108 | Phase 1 | Invoice Type Functional / Scenario Testing | Test Miscellaneous Business Expenses invoice flow | 2026-10-28 | 2026-10-28 | — | — | Team |  |  | Not Started | 0%
109 | Phase 1 | Invoice Type Functional / Scenario Testing | Test Events and Celebrations invoice flow | 2026-10-28 | 2026-10-28 | — | — | Team |  |  | Not Started | 0%
P2 | PHASE 2 | Specialized Invoice Logic & Enterprise Hardening | Dev complete 30-Oct-2026 ¦ Functional tests 04–06 Nov ¦ Phase 2 E2E + full regression 10–13 Nov ¦ LD/Retention/Advance/WHT/VAT, specialized invoices, biometric, reporting, audit/security, reliability. | 2026-09-17 | 2026-11-13 | — | — | Team |  |  | Not Started | 0%
110 | Phase 2 | Liquidated Damages | Finalize and implement LD / 17-Incoterm calculation rules and validate LD scenarios | 2026-10-01 | 2026-10-05 | — | — | Sabrina |  |  | Not Started | 0%
111 | Phase 2 | Retention | Retention calculation and recovery tracking for applicable invoices | 2026-10-13 | 2026-10-14 | — | — | Natheera |  |  | Not Started | 0%
112 | Phase 2 | Advance Payment | Advance-payment recovery calculation and tracking for applicable invoices | 2026-10-06 | 2026-10-07 | — | — | Sabrina |  |  | Not Started | 0%
113 | Phase 2 | WHT / Treaty | WHT, offshore/treaty and withholding-condition calculation | 2026-10-08 | 2026-10-12 | — | — | Sabrina |  |  | Not Started | 0%
114 | Phase 2 | VAT / Faktur Pajak | VAT/tax-document validation including Faktur Pajak format, age, uniqueness and tax rules | 2026-10-15 | 2026-10-16 | — | — | Natheera |  |  | Not Started | 0%
115 | Phase 2 | Specialized Invoice Logic | Manpower N-way reconciliation rules engine — timesheet, manhour summary, WPC/BA, biometric, SES & invoice | 2026-10-22 | 2026-10-26 | — | — | Sabrina |  |  | Not Started | 0%
116 | Phase 2 | Specialized Invoice Logic | Manpower — extraction/config for timesheet, manhour summary & WPC/BA, biometric data mapping and result UI | 2026-10-27 | 2026-10-29 | — | — | Sabrina |  |  | Not Started | 0%
117 | Phase 2 | Specialized Invoice Logic | Civil Contractor progress/WPC, SES, retention, advance and LD-related validation | 2026-10-13 | 2026-10-15 | — | — | Sabrina |  |  | Not Started | 0%
118 | Phase 2 | Specialized Invoice Logic | Catering / Camp / Housekeeping attendance, meal and service reconciliation | 2026-10-16 | 2026-10-20 | — | — | Sabrina |  |  | Not Started | 0%
119 | Phase 2 | Specialized Invoice Logic | Natural Gas tier / benchmark pricing rules & invoice reconciliation | 2026-10-21 | 2026-10-22 | — | — | Rahul |  |  | Not Started | 0%
120 | Phase 2 | Specialized Invoice Logic | Natural Gas — configuration, UI & result presentation | 2026-10-23 | 2026-10-26 | — | — | Rahul |  |  | Not Started | 0%
121 | Phase 2 | Specialized Invoice Logic | Composite PO material/service reconciliation rules & WHT-on-service handling | 2026-10-27 | 2026-10-28 | — | — | Rahul |  |  | Not Started | 0%
122 | Phase 2 | Specialized Invoice Logic | Composite PO — configuration, UI & result presentation | 2026-10-29 | 2026-10-30 | — | — | Rahul |  |  | Not Started | 0%
123 | Phase 2 | Biometric Integration | Secured biometric/attendance inbound API, normalization and missing-data/manual-verification fallback | 2026-09-22 | 2026-09-24 | — | — | Rahul |  |  | Not Started | 0%
124 | Phase 2 | Dashboard & Reporting | AP KPI/workload dashboard, exception/SLA/approval operational views and CSV/Excel exports | 2026-10-15 | 2026-10-26 | — | — | Khalid |  |  | Not Started | 0%
125 | Phase 2 | Audit & Logging | Audit & logging — design review and Azure log/retention setup | 2026-10-12 | 2026-10-12 | — | — | Pranay |  |  | Not Started | 0%
126 | Phase 2 | Security & API Controls | API/data controls — API/file authorization, request validation, secrets/masking, data integrity & concurrency | 2026-09-25 | 2026-09-30 | — | — | Rahul |  |  | Not Started | 0%
127 | Phase 2 | Security & API Controls | Security — UI & file-access behavior validation | 2026-11-04 | 2026-11-05 | — | — | Tester 1 |  |  | Not Started | 0%
128 | Phase 2 | Security & API Controls | Security — architecture & security review | 2026-10-19 | 2026-10-19 | — | — | Pranay |  |  | Not Started | 0%
129 | Phase 2 | Scheduler & Reliability | Background schedulers, checkpointing, locking, retry/backoff, dead-letter, replay & recovery — backend | 2026-10-20 | 2026-10-22 | — | — | Pranay |  |  | Not Started | 0%
130 | Phase 2 | Scheduler & Reliability | Scheduler & reliability — notification/UI recovery flow validation | 2026-11-05 | 2026-11-06 | — | — | Tester 2 |  |  | Not Started | 0%
131 | Phase 2 | Scheduler & Reliability | Scheduler & reliability — resilience design review | 2026-10-23 | 2026-10-23 | — | — | Pranay |  |  | Not Started | 0%
132 | Phase 2 | VAT / Faktur Pajak | Integrate DJP/Coretax API for Faktur Pajak validation | 2026-10-19 | 2026-10-22 | — | — | Natheera |  |  | Not Started | 0%
133 | Phase 2 | Liquidated Damages | Build LD Waiver form, DoA approval and Special GL J reclass | 2026-10-23 | 2026-10-27 | — | — | Natheera |  |  | Not Started | 0%
134 | Phase 2 | Advance Payment | Build Advance Request and Settlement forms with DoA approval and accounting entries | 2026-10-14 | 2026-10-19 | — | — | Anas |  |  | Not Started | 0%
135 | Phase 2 | Dashboard & Reporting | Build reports R-01 to R-08 with Excel/PDF export | 2026-10-20 | 2026-10-26 | — | — | Anas |  |  | Not Started | 0%
136 | Phase 2 | WHT / Treaty | Build COR / DGT register screen with expiry tracking | 2026-10-27 | 2026-10-28 | — | — | Anas |  |  | Not Started | 0%
137 | Phase 2 | Civil Works | Build IUJK / SBU register screen with expiry tracking | 2026-10-29 | 2026-10-30 | — | — | Anas |  |  | Not Started | 0%
138 | Phase 2 | Liquidated Damages | Build LD / 17-Incoterm matrix screen | 2026-10-27 | 2026-10-28 | — | — | Khalid |  |  | Not Started | 0%
139 | Phase 2 | Specialized Invoice Logic | Build Natural Gas price tier matrix screen (LPG / Ammonia) | 2026-10-29 | 2026-10-30 | — | — | Khalid |  |  | Not Started | 0%
140 | Phase 2 | Approval Workflow | Build standalone Berita Acara / WPC record, DoA approval, SharePoint save and PO linking | 2026-10-28 | 2026-10-30 | — | — | Natheera |  |  | Not Started | 0%
141 | Phase 2 | Performance | Run performance and load testing (30 min / 2 hr processing, 25 concurrent users) | 2026-11-04 | 2026-11-06 | — | — | Tester 3 |  |  | Not Started | 0%
142 | Phase 2 | Phase 2 Consolidated E2E & Phase 1 Regression | Phase 2 end-to-end regression with full Phase 1 regression, bug fixes and retest | 2026-11-10 | 2026-11-13 | — | — | Tester 1, Tester 2, Tester 3 |  |  | Not Started | 0%
143 | Phase 2 | Specialized Invoice Functional / Scenario Testing | Test Manpower invoice flow | 2026-11-04 | 2026-11-04 | — | — | Tester 3 |  |  | Not Started | 0%
144 | Phase 2 | Specialized Invoice Functional / Scenario Testing | Test Civil Works (Construction) invoice flow | 2026-11-04 | 2026-11-04 | — | — | Tester 1 |  |  | Not Started | 0%
145 | Phase 2 | Specialized Invoice Functional / Scenario Testing | Test Catering invoice flow | 2026-11-05 | 2026-11-05 | — | — | Tester 2 |  |  | Not Started | 0%
146 | Phase 2 | Specialized Invoice Functional / Scenario Testing | Test Housekeeping invoice flow | 2026-11-05 | 2026-11-05 | — | — | Tester 3 |  |  | Not Started | 0%
147 | Phase 2 | Specialized Invoice Functional / Scenario Testing | Test Composite PO invoice flow | 2026-11-06 | 2026-11-06 | — | — | Tester 1 |  |  | Not Started | 0%
148 | Phase 2 | Specialized Invoice Functional / Scenario Testing | Test Natural Gas invoice flow | 2026-11-06 | 2026-11-06 | — | — | Tester 2 |  |  | Not Started | 0%
149 | SIT | SIT Preparation & Deployment | Prepare SIT build, test data, expected results and deploy/validate the SIT environment. | 2026-11-16 | 2026-11-16 | — | — | Tester 1, Tester 2, Tester 3 |  |  | Not Started | 0%
150 | SIT | Internal SIT / Full Regression | Run internal full-stack, AI, SAP/RPA, business-rule, security and regression suite across Phase 1 + Phase 2. | 2026-11-17 | 2026-11-17 | — | — | Tester 1, Tester 2, Tester 3 |  |  | Not Started | 0%
151 | SIT | Security Testing | Run security / penetration testing and complete CSOC checklist | 2026-11-16 | 2026-11-19 | — | — | Pranay |  |  | Not Started | 0%
152 | SIT | ESSA SIT / UAT Readiness | Execute ESSA pre-UAT verification, retest resolved defects and confirm UAT entry criteria. | 2026-11-18 | 2026-11-18 | — | — | Tester 1, Tester 2, Tester 3 |  |  | Not Started | 0%
153 | UAT | UAT / Defect Resolution / Sign-Off | Execute formal UAT, manage defects, perform regression/retest and obtain UAT sign-off. | 2026-11-19 | 2026-11-25 | — | — | Tester 1, Tester 2, Tester 3, ESSA |  |  | Not Started | 0%
154 | Production Deployment | Operations Readiness | Prepare operations runbook and support handover | 2026-11-20 | 2026-11-23 | — | — | Pranay |  |  | Not Started | 0%
155 | Production Deployment | Training | Prepare user manual and conduct user training | 2026-11-12 | 2026-11-18 | — | — | Robinson |  |  | Not Started | 0%
156 | Production Deployment | Production Readiness & Cutover | Production readiness — environment validation, release/branch freeze, SAP/RPA connectivity checks & cutover checklist | 2026-11-26 | 2026-11-27 | — | — | Pranay |  |  | Not Started | 0%
157 | Production Deployment | Production Readiness & Cutover | Production readiness — backend/DB/config migration cutover & smoke test support | 2026-11-26 | 2026-11-27 | — | — | Rahul |  |  | Not Started | 0%
158 | Production Deployment | Production Readiness & Cutover | Production readiness — UI/configuration validation & smoke test support | 2026-11-26 | 2026-11-27 | — | — | Sabrina |  |  | Not Started | 0%
159 | Production Deployment | Production Readiness & Cutover | Production readiness — SAP integration connectivity verification | 2026-11-26 | 2026-11-27 | — | — | Anas |  |  | Not Started | 0%
160 | Production Deployment | Production Go-Live | Go-Live — deploy approved production release | 2026-11-30 | 2026-11-30 | — | — | Pranay |  |  | Not Started | 0%
161 | Production Deployment | Production Go-Live | Go-Live — backend smoke test, integration verification & rapid fix support | 2026-11-30 | 2026-11-30 | — | — | Rahul |  |  | Not Started | 0%
162 | Production Deployment | Production Go-Live | Go-Live — UI smoke test & rapid fix support | 2026-11-30 | 2026-11-30 | — | — | Sabrina |  |  | Not Started | 0%
163 | Production Deployment | Production Go-Live | Go-Live — SAP/RPA integration validation | 2026-11-30 | 2026-11-30 | — | — | Anas |  |  | Not Started | 0%
164 | Production Deployment | Production Go-Live | Go-Live — business confirmation & hypercare handover acceptance | 2026-11-30 | 2026-11-30 | — | — | ESSA |  |  | Not Started | 0%
165 | Hypercare | Hypercare & Stabilization | Hypercare support, defect fixing and stabilization after go-live | 2026-12-01 | 2026-12-14 | — | — | Rahul, Sabrina, Anas, Natheera, Khalid |  |  | Not Started | 0%
166 | Project Management | Project Management | Project governance, status reporting, RAID/dependency management, client coordination, release governance and closure. | 2026-07-28 | 2027-01-13 | 2026-07-28 | — | Robinson |  |  | In Progress | —

## 📝 Daily Scrum Log
ESSA EAPA — Daily Scrum Log
Update daily. Date ¦ Employee ¦ Module ¦ Done Yesterday ¦ Today's Plan ¦ Any Blocker?
Date | Employee | Module | Task ID | Done Yesterday | Today's Plan | Any Blocker?
02-Sep-26 | Rahul | Auth / RBAC |  | Completed Entra ID SSO POC and RBAC role mapping. | Start Admin Config Management — Invoice Category Config. | None
02-Sep-26 | Sabrina | Invoice Ingestion |  | Completed email ingestion and SharePoint folder monitoring. | Continue attachment controls and duplicate detection. | Document type validation not yet implemented.
02-Sep-26 | Khalid | Dashboard |  | Completed invoice list filtering. | Work on invoice timeline sequence flow and search bar. | None
02-Sep-26 | Natheera | RPA / SAP |  | Reviewed MIRO and FB60 transaction flows. | Set up Power Automate Desktop bot environment. | SAP GUI scripting not yet enabled — waiting for ESSA SAP team.
2026-09-09 | Sabrina | ESSA |  | - continue work on validation configuration integration in main flow of invoice validation - Prepared test data of SAP data to validate with dynamic rules | - Take one invoice type, Man Power, work on end to end validation completion. (SAP Field and document availability validation). Take reference from POC and test if everything working fine, as now its dynamic fields and dynamic document availability rules. | NA
2026-09-09 | Suganth | ESSA |  | - Worked on UI for Inbound email visibility. | - TBD | - Request for review of Test CAses
2026-09-09 | Rahul | ESSA |  | - SLA admin Config is done - SLA scheduler integration to execute admin config in main invoice flow, started working on that | - SLA scheduler integration to execute admin config in main invoice flow | NA
2026-09-09 | Khalid | ESSA |  | - Busy in working with Shafeeq on other tasks | - work on unit test case
2026-09-10 | Rahul | ESSA |  | - Deployed the BE and FE Essa related changes on new RIL server. - Changed the theme and color as per Avensys - Restored the DB - Tested everything | - will work on the SLA related remaining tasks | NA
2026-09-10 | Sabrina | ESSA |  | - Continued working on document availability and sap field mapping validation. - Worked on integrating the validation logic for document validation through sending of email notifications to the vendor and sorting invoices into draft states if documents are unavailable. Testing and fixing any issues found while testing. | - Continued on working on testing and fixing of document availability and SAP field mapping validation. - Testing with new additional fields in the SAP field if validations are being checked correctly. | NA
2026-09-10 | Suganth | ESSA
2026-09-10 | Khalid | ESSA |  | -completed integrating Audit logs page fron suganths, Edited the pusrchase oprder and teh vendors page sizing and the tile according to the Suganths work | continue to work on any other UI discrepency found in smaller screen
2026-09-10 | Natheera | ESSA
2026-09-11 | Sabrina | ESSA | 41 | - Completed validation integration for SAP Field mapping validation and document availability validation - Started work on the Audit Log for invoice processing | - Continue working on the Audit Log for invoice processing | NA
2026-09-11 | Suganth | ESSA
2026-09-11 | Rahul | ESSA | 23 | - Created a scheduler to read SLA config and conrrespondingly send the notifications for the invoices - Right now, doing the testing of all the events of invoices and try to link them with SLA | - will complete SLA related testing. - will Start work on the new task
2026-09-11 | Khalid | ESSA
2026-09-14 | Sabrina | ESSA | 45 | - Worked on Audit Logs for both login and invoice logging. | - Continue working on Audit Logs for both login and invoice logging, to complete today. | Tokens are unavailable.
2026-09-14 | Suganth | ESSA
2026-09-14 | Rahul | ESSA | 26 | - Completed 21,22,23 SLA related tasks. - Working on the team approval mechanism | - Will continue to work on Teams approval mechanism
2026-09-14 | Khalid | ESSA
2026-09-15 | Sabrina | ESSA | 45 | - Continued working on Audit Logs but had issues with testing and continuing with invoice processing audit logging as the tokens are unavailable. |  | Tokens are unavailable.
2026-09-15 | Suganth | ESSA
2026-09-15 | Rahul | ESSA | 26
2026-09-15 | Khalid | ESSA |  |  | - Work on invoice processing end to end testing for Civil Contract invoice.
2026-09-16 | Sabrina | ESSA | 45 | - Completed Audit Log for Invoice Processing and Login logs
2026-09-16 | Suganth | ESSA
2026-09-16 | Rahul | ESSA | 54, 56 | - Worked on Invoice Orchestration, created the required tables, and started implementing the backend and frontend changes.
2026-09-16 | Khalid | ESSA
2026-09-17 | Sabrina | ESSA | 52 | - Worked on invoice processing end to end testing for Civil Contract invoice. | - Continue working on end to end testing for Civil Contract.
2026-09-17 | Suganth | ESSA
2026-09-17 | Rahul | ESSA
2026-09-17 | Khalid | ESSA
2026-09-18 | Sabrina | ESSA | 52 | - Created new document on required fields and categories to set up full extraction for other category types.
2026-09-18 | Suganth | ESSA
2026-09-18 | Rahul | ESSA |  |  | On Leave
2026-09-18 | Khalid | ESSA
2026-09-21 | Sabrina | ESSA | 52 | - Worked on referencing the existing requirement gathering for end to end testing for the Civil Contract. - Connected with Nitesh with Robin and Pranay for better understanding on the requirements.
2026-09-21 | Suganth | ESSA |  |  | On Leave
2026-09-21 | Rahul | ESSA |  | On Leave | On Leave
2026-09-21 | Khalid | ESSA
2026-09-22 | Sabrina | ESSA | 52 | - Call with Anas on CSV clarification - Worked on
2026-09-23 | Sabrina | ESSA |  | - Had clarification call with Nitish on the requirements for categorising PO and Non-PO - Worked on testing the differences between Non-PO invoices - Hotel Invoices

## Sheet2 (hidden)
Phase | Workstream | Activity | Task
Phase 2 | Full Stack | Req. 4 Development | Develop Req. 4-specific frontend functionality
Phase 2 | Full Stack | Req. 4 Development | Develop Req. 4-specific backend/API functionality
Phase 2 | Full Stack | Req. 5 Development | Develop Req. 5-specific frontend functionality
Phase 2 | Full Stack | Req. 5 Development | Develop Req. 5-specific backend/API functionality
Phase 2 | Full Stack | Req. 6 Development | Develop Req. 6-specific frontend functionality
Phase 2 | Full Stack | Req. 6 Development | Develop Req. 6-specific backend/API functionality
Phase 2 | Full Stack | Invoice Posting | Develop invoice posting workflow for Phase 2
Phase 2 | Full Stack | Invoice Posting | Implement posting status and response handling
Phase 2 | Full Stack | Invoice Posting | Implement posting failure/exception handling
Phase 2 | Full Stack | Re-match | Develop Re-match functionality, if applicable to Req. 4-6
Phase 2 | Full Stack | Writeback | Develop Writeback functionality, if applicable to Req. 4-6
Phase 2 | RPA | RPA Posting Automation | Develop MIRO posting bot
Phase 2 | RPA | RPA Posting Automation | Develop FB60 posting bot
Phase 2 | RPA | RPA Document Automation | Develop GOS automation
Phase 2 | RPA | RPA Re-match Automation | Develop Re-match bot
Phase 2 | RPA | RPA Writeback Automation | Develop Writeback bot
Phase 2 | RPA | RPA Integration | Integrate posting bots with EAPA
Phase 2 | RPA | RPA Integration | Implement bot response/status update to EAPA
Phase 2 | RPA | RPA Exception Handling | Implement posting bot exception handling
Phase 2 | RPA | RPA Testing | Perform unit testing of Phase 2 bots
Phase 2 | SAP | SAP Posting Integration | Finalise SAP posting interface for Phase 2
Phase 2 | SAP | SAP Posting Integration | Develop required SAP posting interface/programs
Phase 2 | SAP | MIRO Integration | Implement MIRO integration
Phase 2 | SAP | FB60 Integration | Implement FB60 integration
Phase 2 | SAP | GOS Integration | Implement GOS integration
Phase 2 | SAP | Re-match Integration | Implement SAP support for Re-match
Phase 2 | SAP | Writeback Integration | Implement SAP writeback
Phase 2 | SAP | Posting Response | Implement SAP posting response/status handling
Phase 2 | SAP | Error Handling | Implement SAP posting error handling
Phase 2 | SAP | SAP Testing | Perform SAP posting/interface testing
Phase 2 | AI | AI Enhancement | Implement additional extraction fields required for Req. 4-6
Phase 2 | AI | AI Enhancement | Enhance extraction logic for additional Phase 2 invoice types/scenarios
Phase 2 | AI | AI Integration | Integrate AI enhancements with existing EAPA flow
Phase 2 | AI | AI Testing | Test additional Phase 2 invoice scenarios
Phase 2 | Business Rules | Additional Business Rules | Implement only new business rules applicable to Req. 4-6
Phase 2 | Business Rules | Calculation Enhancement | Implement additional calculation logic required for Req. 4-6
Phase 2 | Business Rules | Validation Enhancement | Implement additional validation rules required for Req. 4-6
Phase 2 | Integration | FS-RPA Integration | Integrate Phase 2 invoice posting workflow with RPA
Phase 2 | Integration | RPA-SAP Integration | Integrate posting bots with SAP
Phase 2 | Integration | FS-SAP Integration | Integrate Phase 2 posting functionality with SAP
Phase 2 | Integration | Writeback Integration | Integrate SAP/RPA posting response and writeback with EAPA
Phase 2 | Integration | End-to-End Integration | Complete Phase 2 end-to-end invoice posting flow
Phase 2 | Integration | Error Handling | Validate end-to-end exception and failure handling
Phase 2 | Testing | Unit Testing | Complete FS unit testing for Req. 4-6
Phase 2 | Testing | Unit Testing | Complete RPA unit testing
Phase 2 | Testing | Unit Testing | Complete SAP interface testing
Phase 2 | Testing | Integration Testing | Test FS-RPA integration
Phase 2 | Testing | Integration Testing | Test RPA-SAP integration
Phase 2 | Testing | Integration Testing | Test FS-SAP integration
Phase 2 | Testing | Integration Testing | Test posting and writeback flow
Phase 2 | Testing | End-to-End Testing | Execute complete Phase 2 invoice posting scenarios
Phase 2 | SIT | SIT Preparation | Prepare Req. 4-6 SIT scenarios
Phase 2 | SIT | SIT Preparation | Prepare Phase 2 test invoices
Phase 2 | SIT | SIT Preparation | Prepare Phase 2 test data
Phase 2 | SIT | SIT Preparation | Prepare SAP posting test data
Phase 2 | SIT | SIT Preparation | Prepare expected results
Phase 2 | SIT | SIT Deployment | Deploy Phase 2 SIT build
Phase 2 | SIT | SIT Deployment | Validate Phase 2 SIT environment
Phase 2 | ESSA Testing | ESSA SIT | Execute ESSA Phase 2 test scenarios
Phase 2 | ESSA Testing | Defect Management | Log and classify ESSA defects
Phase 2 | Development | Defect Fixing | Fix Phase 2 defects
Phase 2 | Testing | Regression Testing | Perform regression testing against Phase 1 functionality
Phase 2 | ESSA Testing | Retesting | ESSA retesting of resolved defects
Phase 2 | Project Management | Phase 2 Closure | Obtain Phase 2 acceptance and sign-off

## 📊 Summary
ESSA EAPA — Development Summary
STATUS SUMMARY |  | PROGRESS SUMMARY
Total Tasks | 98 | Overall % Complete
Completed |  | Tasks Remaining
In Progress
Not Started
Blocked
On Hold
MODULE BREAKDOWN
Module | Tasks | Completed
Application Foundation | 2 | 1
Authentication & Access | 3 | 3
Admin & Configuration | 8 | 0
Invoice Ingestion | 7 | 0
Vendor Communication | 4 | 0
Document Management | 3 | 0
Invoice Processing Orchestration | 4 | 0
Azure OpenAI Processing | 5 | 0
HITL / Extraction Review | 3 | 0
Core Validation Engine | 7 | 0
Exception Management | 2 | 0
Category-Specific Processing | 7 | 0
Financial Adjustments & Tax | 3 | 0
Vendor Controls | 2 | 0
Biometric Integration | 2 | 0
Workflow & Approval | 6 | 0
SLA & Notifications | 3 | 0
SAP Reference Data Integration | 5 | 0
SAP Parking / RPA | 7 | 0
SAP Extraction | 6 | 0
Dashboard & Reporting | 3 | 0
Audit, Logging & Monitoring | 3 | 0
Security & API Controls | 3 | 0
Email Template Config | 1 | 0
Scheduler & Reliability | 1 | 0

## Status Master (hidden)
# | Status | Applies To | When to Use | Team Responsible
1 | Not Started | FS + RPA | Task not yet begun | Rahul, Sabrina
2 | In Progress | FS + RPA | Actively being worked on | Rahul
3 | Dev Complete | FS + RPA | Development done — FE + BE + RPA flow fully built. Ready for internal testing | Sabrina
4 | Code Review | FS | Code submitted for peer review before merge | Suganth
5 | Bot Testing | RPA | RPA bot flow built and being tested locally against SAP Dev by Natheera | Khalid
6 | Fixed | FS + RPA | Bug or defect fixed — awaiting retest | Robinson
7 | Blocked | FS + RPA | Cannot proceed — blocker in Blocker column | Anas
8 | Awaiting ESSA Input | FS + RPA | Dev ready to proceed but waiting for ESSA confirmation/input/access | Robinson, Anas, Pranay
9 | On Hold | FS + RPA | Deliberately paused — dependency or decision pending | Natheera
10 | Integration Testing | FS + RPA | End-to-end integration testing between FE, BE, RPA and SAP | ESSA
11 | Integration Failed | FS + RPA | Integration testing raised issues — back to fix | Rahul, Sabrina
12 | SIT | FS + RPA | System Integration Testing in progress | Pranay
13 | SIT Failed | FS + RPA | SIT defects raised — back to dev for fix | SIT defects raised — back to dev for fix
14 | UAT | FS + RPA | In User Acceptance Testing by ESSA
15 | UAT Failed | FS + RPA | UAT defects raised — back to dev for fix
16 | Completed | FS + RPA | Fully done — tested, signed off, closed
17 | FE Done | FS | Front end done
17 | BE Done | FS | Backend done
Lifecycle Flow — Visual
Not Started
↓
In Progress
↓
Dev Complete ──────────────────────────────────────────────────→ Fixed (if bug)
↓ ↑
Code Review (FS) / Bot Testing (RPA) │
↓ │
Integration Testing ─────────────────────────────────────── Integration Failed
↓ ↑
SIT ──────────────────────────────────────────────────────── SIT Failed
↓ ↑
UAT ──────────────────────────────────────────────────────── UAT Failed
↓
Completed

## 📦 Delivery Tracker (hidden)
ESSA EAPA — Development Delivery Tracker ¦ Task-Level
Each row = one deliverable task. Update Status, % Complete, Actual dates and Remarks weekly. Blocker column must be filled when status = Blocked.
# | Module | Sub-Module | Task / Deliverable | Scope / Completion Criteria | Planned Start | Planned End | Actual Start | Actual End | Assignee | Status | % Done | Layer | Blocker / Pending Input | Remarks
1 | Application Foundation | Application Codebase | React, Node.js/TypeScript & PostgreSQL app foundation | Establish React FE, Node.js/TS BE, common API patterns, shared libraries, PostgreSQL connectivity, migrations and transaction baseline. | 31-Aug-26 | 04-Sep-26 | 31-Aug-26 | 31-Aug-26 | Rahul | Completed | 100% | FE + BE + DB
2 | Application Foundation | Environment & Delivery | Env. config, CI/CD and deployment baseline | Externalize env settings/secrets, build/deployment pipeline, DB migration promotion and versioned artifact deployment for DEV/UAT/PROD. | 07-Sep-26 | 14-Sep-26 |  |  |  | Not Started | 0% | BE + Integration
3 | Authentication & Access | SSO — POC | SAP SSO POC | SAP SSO POC | 2026-08-20 | 2026-08-21 | 2026-08-20 | 2026-08-21 | Rahul | Completed | 100% | BE + FE
3 | Authentication & Access | SSO — POC | Microsoft Entra ID SSO POC | POC for SSO integration with Entra ID. | 2026-08-24 | 2026-08-26 | 2026-08-24 | 2026-08-26 | Rahul | Completed | 100% | BE + FE
4 | Authentication & Access | SSO & Session | Direct Portal Entry with SAP SSO | Support approved application launch paths through the Launchpad and direct portal URL, with appropriate access validation. | 2026-08-24 | 2026-08-26 | 2026-08-24 | 2026-08-26 | Rahul | Completed | 100% | BE + FE
4 | Authentication & Access | SSO & Session | Fiori & Direct Portal Entry | Support approved application launch paths through the Fiori Launchpad and direct portal URL, with appropriate access validation. | 2026-08-27 | 2026-08-28 | 2026-08-27 | 2026-08-28 | Rahul | Completed | 100% | BE + FE
5 | Authentication & Access | SSO & Session | Entra ID SSO Integration | Integrate Microsoft Entra ID using OIDC/OAuth for secure user authentication and seamless single sign-on. | 2026-08-27 | 2026-08-28 | 2026-08-27 | 2026-08-28 | Rahul | Completed | 100% | BE + FE
6 | Authentication & Access | SSO & Session | Session & Logout Management | Implement token/session expiry, session validation, automatic h | 2026-08-31 | 2026-09-01 | 2026-08-31 | 2026-09-01 | Rahul | Completed | 100% | BE + FE
7 | Authentication & Access | RBAC & User Admin | Role mapping, authorization and user/role administration | Map Entra identities/groups to EAPA roles. Enforce page, API, action and data-scope permissions. Provide controlled user-role admin. | 2026-08-31 | 2026-09-01 | 2026-08-31 | 2026-09-01 | Rahul | Completed | 100% | BE + FE + DB
8 | Admin & Configuration | Invoice Category Config | Invoice category and subcategory master | Create UI/API/data model for categories, subcategories, codes, descriptions and active status. | 07-Sep-26 | 16-Sep-26 | 2026-08-17 | 2026-08-19 | Sabrina | Completed | 100% | FE + BE + DB | INP-001 — Category list from ESSA pending
9 | Admin & Configuration | Document Matrix Config | Document types, required/conditional document matrix | Configure document types, mandatory/optional/conditional applicability by category and processing modes (AVAILABILITY_ONLY, EXTRACT_ONLY, EXTRACT_AND_VALIDATE). | 07-Sep-26 | 16-Sep-26 | 2026-08-17 | 2026-08-19 | Sabrina | Completed | 100% | FE + BE + DB | INP-002 — Document matrix from ESSA pending
10 | Admin & Configuration | Field & Schema Config | Invoice/document field and extraction schema config | Configure fields, data types, mandatory flags, source document, normalization rules and validation applicability by category/document. | 07-Sep-26 | 16-Sep-26 | 2026-08-12 | 2026-08-14 | Sabrina | Completed | 100% | BE + DB | INP-003 — Annexure B from ESSA pending
11 | Admin & Configuration | Prompt Config | Category/document prompt template configuration | Maintain extraction prompts, instructions, schema bindings and model parameters by category/document. | 07-Sep-26 | 16-Sep-26 | 2026-08-17 | 2026-08-18 | Sabrina | Completed | 100% | BE + DB | INP-003 — Annexure B from ESSA pending
12 | Admin & Configuration | Validation Config | Validation rule, tolerance and outcome-code metadata | Configure deterministic rule applicability, parameters, tolerances, outcome/error codes and rule versions. | 07-Sep-26 | 16-Sep-26 | 2026-08-19 |  | Sabrina | In Progress | 0% | BE + DB | INP-002, INP-007, INP-008 from ESSA pending
13 | Admin & Configuration | SLA Configuration | SLA & Due-Date Settings | Configure SLA rules, due dates, business hours, and applicable SLA parameters. | 2026-09-07 | 2026-09-10 | 2026-09-07 |  | Rahul | In Progress | 60% | BE + FE + DB | INP-016 — SLA confirmation from ESSA pending
14 | Admin & Configuration | SLA Configuration | Reminder Schedules | Configure reminder intervals, notification timings, and recipients for approaching SLA due dates. | 2026-09-07 | 2026-09-10 | 2026-09-07 |  | Rahul | In Progress | 60% | BE + FE + DB | INP-016 — SLA confirmation from ESSA pending
15 | Admin & Configuration | SLA Configuration | Escalation Schedules | Configure escalation rules, escalation levels, timings, and recipients for approaching or breached SLAs. | 2026-09-07 | 2026-09-10 | 2026-09-07 |  | Rahul | In Progress | 60% | BE + FE + DB
16 | Admin & Configuration | Communication Configuration | Email Templates | Create Email Template UI – Design and implement the UI to create, edit, view, and manage static email templates used for SLA reminders, escalations, and other system communications. | 2026-09-02 | 2026-09-04 | 2026-09-02 | 2026-09-04 | Rahul | Completed | 100% | BE + FE + DB | INP-016 — SLA confirmation from ESSA pending
| Admin & Configuration | Communication Configuration | Email Templates | Email Template Management & Integration – Implement the backend/API functionality to store, retrieve, update, and manage email templates, and integrate the templates with the relevant SLA reminder and escalation communication flows. | 2026-09-02 | 2026-09-04 | 2026-09-02 | 2026-09-04 | Rahul | Completed | 100% | BE + FE + DB
17 | Admin & Configuration | Communication Configuration | Teams & In-App Templates | Create and manage static Microsoft Teams and in-app notification templates for system communications. |  |  |  |  | Rahul
18 | Admin & Configuration | Workflow Config | DoA, approval and Tax workflow configuration | Configure approval stages, DoA thresholds/hierarchy, Tax applicability, WPC approval applicability and workflow versions. | [5 empty] | Not Started | 0% | BE + DB | INP-004 — DoA matrix from ESSA pending
19 | Admin & Configuration | Config Governance | Draft, review, approve, publish and version governance | Controlled config lifecycle with immutable published versions, effective dates, activation and rollback/history. | [5 empty] | Not Started | 0% | BE + DB
76 | SLA & Notifications | SLA Engine | SLA Configuration & Rule Evaluation | Read published SLA configuration and evaluate applicable SLA rules based on invoice, stage, and business conditions. | 2026-09-11 | 2026-09-16 |  |  | Rahul | Not Started | 0% | BE + FE + DB | INP-016 — SLA definitions from ESSA AP
77 | SLA & Notifications | SLA Engine | Due-Date & SLA Calculation | Calculate invoice/stage due dates and SLA checkpoints using configured rules, calendars, working hours, and invoice/stage attributes. | 2026-09-11 | 2026-09-16 |  |  | Rahul | Not Started | 0% | BE + FE + DB
78 | SLA & Notifications | Reminder & Escalation | Reminder Scheduling | Generate and schedule configured reminders for pending reviews, approvals, and other SLA-driven activities. | 2026-09-11 | 2026-09-16 |  |  | Rahul | Not Started | 0% | BE + FE + DB
| SLA & Notifications | Reminder & Escalation | Escalation & Vendor-Chase Scheduling | Generate configured escalations for SLA breaches/thresholds and schedule vendor-chase notifications for missing documents or pending actions. | 2026-09-11 | 2026-09-16 |  |  | Rahul | Not Started | 0% | BE + FE + DB
| SLA & Notifications | Notification Delivery | Email Notification Delivery | Implement Email notification delivery, including recipient resolution, template rendering, delivery-status tracking, and retry handling. | 2026-09-11 | 2026-09-16 |  |  | Rahul | Not Started | 0% | BE + FE + DB
| SLA & Notifications | Notification Delivery | Teams & In-App Notification Delivery | Implement Microsoft Teams and in-app notification delivery, including recipient resolution, template rendering, delivery-status tracking, and retry handling. | 2026-09-11 | 2026-09-16 |  |  | Rahul | Not Started | 0% | BE + Integration
20 | Invoice Ingestion | Email Ingestion UI Handling | AP mailbox visibility, manual polling | View details of status of the inbound emails, manually poll emails and filter email statuses |  |  | 25-Aug-26 | 2026-09-08 | Sabrina | Completed | 100%
21 | Invoice Ingestion | Email Ingestion | AP mailbox connectivity, polling and checkpointing | Connect to AP mailbox, poll/sync messages through controlled checkpoints and capture source metadata. | 25-Aug-26 |  | 25-Aug-26 | 2026-08-27 | Sabrina | In Progress | 80% | BE + Integration | INP-014 — Final mailbox/SharePoint config from ESSA IT | Continuing to test with other invoice types
22 | Invoice Ingestion | Email Registration | Email, attachment and invoice/bundle registration | Register email metadata, supported attachments and initial invoice/bundle records. | 25-Aug-26 |  | 25-Aug-26 | 26-Aug-26 | Sabrina | In Progress | 80% | BE + DB |  | Continuing to test with other invoice types
23 | Invoice Ingestion | Attachment Controls | File controls, ZIP handling and one-PDF-one-invoice rule | Validate extension/content, size and safety; expand ZIPs; enforce supported document policy and reject multi-invoice PDFs. | 25-Aug-26 |  | 25-Aug-26 | 2026-08-28 | Sabrina | In Progress | 80% | BE |  | Validations for document types not yet implemented
24 | Invoice Ingestion | Subject & Correlation | Email subject parsing, category/PO hints and DOCREQ correlation | Parse subject for category hints, PO/reference info and document-request correlation. | 25-Aug-26 |  | 25-Aug-26 | 26-Aug-26 | Sabrina | In Progress | 80% | BE |  | Continuing to test with other invoice types
25 | Invoice Ingestion | Duplicate & Idempotency | Duplicate email, file and invoice intake controls | Use message IDs, file hashes and business identifiers to prevent duplicate intake. | 27-Aug-26 |  | 27-Aug-26 | 2026-09-01 | Sabrina | In Progress | 80% | BE + DB |  | Need to keep retesting with multiple documents
26 | Invoice Ingestion | SharePoint Ingestion | SharePoint watch-folder intake | Poll approved SharePoint intake location and route files through common controls. | 27-Aug-26 |  | 27-Aug-26 | 2026-08-28 | Sabrina | In Progress | 80% | BE + Integration | INP-014 — SharePoint config from ESSA IT pending
27 | Invoice Ingestion | Manual Upload (BCP) | Admin-only manual portal upload | Controlled business-continuity upload with metadata, file validation, duplicate checks and audit. | 15-Sep-26 | 24-Sep-26 | 2026-09-08 | 2026-09-08 | Sabrina | Completed | 100% | FE + BE
28 | Vendor Communication | Missing Document Request | Missing mandatory document request case creation | Create uniquely identified request against existing invoice for each missing mandatory/conditional document. | 01-Oct-26 | 14-Oct-26 | 25-Aug-26 |  | Sabrina | In Progress | 70% | BE + DB |  | Email has issue at the moment
29 | Vendor Communication | Vendor Communication Workspace | Controlled vendor email draft, review/edit and send | Generate configured vendor communication draft, allow AP Team review/edit, resolve recipients and send only after permitted action. | 01-Oct-26 | 14-Oct-26 | 25-Aug-26 | 25-Aug-26 | Sabrina | In Progress | 80% | FE + BE
30 | Vendor Communication | DOCREQ Communication | Correlated DOCREQ email generation and send | Generate document-request email using controlled [EAPA][DOCREQ][INV][REQ][DOC] correlation pattern. | 01-Oct-26 | 14-Oct-26 | 2026-09-03 | 2026-09-04 | Sabrina | In Progress | 70% | BE
31 | Vendor Communication | Vendor Response & Replacement | Response correlation, replacement lineage and reprocessing | Correlate vendor reply/replacement to existing invoice/request, retain lineage and resume processing. | 01-Oct-26 | 14-Oct-26 | 2026-09-03 | 2026-09-07 | Sabrina | In Progress | 80% | BE + DB
32 | Document Management | SharePoint Storage | Invoice and supporting-document storage | Store document binaries in approved SharePoint structure; persist only metadata/references in EAPA PostgreSQL. | 17-Sep-26 | 30-Sep-26 | 27-Aug-26 | 2026-08-28 | Sabrina | Completed | 80% | BE + Integration | INP-014 — SharePoint location from ESSA IT
33 | Document Management | Metadata & Lineage | Document metadata, version and replacement lineage | Maintain source, document type, version, active/replaced state, hashes, request relationships and history. | 17-Sep-26 | 30-Sep-26 |  |  |  | Not Started | 0% | BE + DB
34 | Document Management | Secure Document Access | Authorized preview, download and navigation | Role-controlled document list, preview/download and navigation across invoice/supporting/replacement documents. | 17-Sep-26 | 30-Sep-26 |  |  |  | Not Started | 0% | FE + BE
35 | Invoice Processing Orchestration | Invoice Registration | Canonical invoice aggregate and lifecycle initialization | Create canonical invoice identifiers, source relationships and initial Draft status/processing-stage state. | 01-Oct-26 | 14-Oct-26 |  |  |  | Not Started | 0% | BE + DB
36 | Invoice Processing Orchestration | Classification | PO/Non-PO and invoice category classification | Determine PO/Non-PO and category using subject hints, configured rules and GPT assistance with manual-review path. | 01-Oct-26 | 14-Oct-26 |  |  |  | Not Started | 0% | BE + AI | INP-001 — Category list from ESSA pending
37 | Invoice Processing Orchestration | Configuration Resolution | Published configuration snapshot resolution | Resolve category, document matrix, fields, prompts, validation rules, SLA and workflow config as one traceable runtime snapshot. | 01-Oct-26 | 14-Oct-26 |  |  |  | Not Started | 0% | BE + DB
38 | Invoice Processing Orchestration | Stage & Lifecycle Control | End-to-end stage orchestration and lifecycle transitions | Coordinate completeness, extraction, HITL, validation, exception/override, approval/tax, SAP parking and status sync. | 01-Oct-26 | 14-Oct-26 |  |  |  | Not Started | 0% | BE + DB
39 | Azure OpenAI Processing | Azure OpenAI Integration | Azure OpenAI client, deployment and secure connectivity | Integrate Node.js with approved Azure OpenAI deployment including credentials, endpoint, model config and timeout controls. | 17-Sep-26 | 30-Sep-26 |  |  |  | Not Started | 0% | BE + AI
40 | Azure OpenAI Processing | Dynamic Prompting | Dynamic prompt and structured schema generation | Build prompts from category, document type, published field schema, configured instructions and extraction contract. | 17-Sep-26 | 30-Sep-26 |  |  |  | Not Started | 0% | BE + AI | INP-003 — Field schema from ESSA pending
41 | Azure OpenAI Processing | Document Extraction | Native/scanned/image/handwritten document extraction | Process English/Bahasa native PDFs, scanned/image PDFs and handwritten content through Azure OpenAI for structured extraction. | 17-Sep-26 | 30-Sep-26 |  |  |  | Not Started | 0% | BE + AI
42 | Azure OpenAI Processing | Response Normalization | Schema validation, normalization and confidence handling | Validate model output schema and normalize dates, numbers, currencies, text and confidence/uncertainty indicators. | 17-Sep-26 | 30-Sep-26 |  |  |  | Not Started | 0% | BE + AI
43 | Azure OpenAI Processing | AI Reliability & Usage | Retry, throttling, failures and token-usage capture | Implement retry/backoff, throttling, timeout/failure handling and input/output token/usage metadata capture. | 17-Sep-26 | 30-Sep-26 |  |  |  | Not Started | 0% | BE + AI
44 | HITL / Extraction Review | Review Queue | Low-confidence/manual review queue with team routing | Create review queues and assignment/routing for Material, Service, Site or other configured reviewer groups. | 01-Oct-26 | 14-Oct-26 |  |  |  | Not Started | 0% | FE + BE + DB
45 | HITL / Extraction Review | Review Workspace | Document-to-field verification and correction workspace | Display source document preview alongside extracted fields/confidence and allow controlled field corrections. | 01-Oct-26 | 14-Oct-26 |  |  |  | Not Started | 0% | FE + BE
46 | HITL / Extraction Review | Correction Commit | Correction versioning, audit and downstream re-entry | Persist before/after correction values, reviewer identity/reason and re-enter downstream processing from correct stage. | 01-Oct-26 | 14-Oct-26 |  |  |  | Not Started | 0% | BE + DB
47 | Core Validation Engine | Rule Framework | Deterministic validation execution framework | Implement reusable rule execution, context loading, applicability, parameter/tolerance resolution and result persistence. | 01-Oct-26 | 14-Oct-26 |  |  |  | Not Started | 0% | BE + DB
48 | Core Validation Engine | Document Completeness | Mandatory and conditional document completeness validation | Evaluate required/optional/conditional document availability by category and PO terms before extraction continuation. | 01-Oct-26 | 14-Oct-26 |  |  |  | Not Started | 0% | BE + DB | INP-002 — Document matrix from ESSA pending
49 | Core Validation Engine | SAP Reference Matching | PO, GRN and SES header/line reference matching | Validate configured PO/GRN/SES identifiers, line quantities/values and reference attributes against synchronized snapshots. | 01-Oct-26 | 14-Oct-26 |  |  |  | Not Started | 0% | BE + DB | INP-009 — SAP objects from ESSA SAP team
50 | Core Validation Engine | Financial Arithmetic | Quantity, subtotal, amount, VAT/tax arithmetic and reconciliation | Implement deterministic quantity, subtotal, amount, total-excl-tax and VAT/tax arithmetic/reconciliation checks. | 01-Oct-26 | 14-Oct-26 |  |  |  | Not Started | 0% | BE + DB
51 | Core Validation Engine | SES & Tolerance | SES and configured tolerance validation | Implement SES-specific tolerance calculations including invoice subtotal, total excluding VAT, tolerance amount and difference. | 01-Oct-26 | 14-Oct-26 |  |  |  | Not Started | 0% | BE + DB
52 | Core Validation Engine | Cross-Document Validation | N-way and cross-document reconciliation framework | Compare configured fields and calculated values across invoice/supporting documents and synchronized SAP reference data. | 01-Oct-26 | 14-Oct-26 |  |  |  | Not Started | 0% | BE + DB
53 | Core Validation Engine | Validation Outcome | Result aggregation, error catalogue and controlled revalidation | Aggregate individual rule outcomes, assign outcome codes, retain prior runs and support controlled revalidation. | 01-Oct-26 | 14-Oct-26 |  |  |  | Not Started | 0% | BE + DB
54 | Exception Management | Exception Workbench | Processing/validation exception workbench | Provide searchable/filterable exception queue with invoice/document context, failure reason, owner/state and resolution actions. | 15-Oct-26 | 21-Oct-26 |  |  |  | Not Started | 0% | FE + BE
55 | Exception Management | Override & Resolution | Controlled override, remarks, resubmission and re-entry | Allow authorized override of eligible exceptions with mandatory reason; support correction/resubmission and controlled re-entry. | 15-Oct-26 | 21-Oct-26 |  |  |  | Not Started | 0% | FE + BE + DB
56 | Category-Specific Processing | Manpower | Manpower invoice N-way reconciliation | Implement timesheet, manhour summary, WPC/BA, biometric/attendance, SES and invoice reconciliation logic. | 01-Oct-26 | 14-Oct-26 |  |  |  | Not Started | 0% | BE + DB | INP-018 — Biometric interface from ESSA IT; INP-020 — samples from ESSA
57 | Category-Specific Processing | Civil Contractor | Civil contractor progress/WPC validation | Implement progress/WPC, SES, licence/supporting-document, retention, advance and LD-related validation flow. | 01-Oct-26 | 14-Oct-26 |  |  |  | Not Started | 0% | BE + DB | INP-008 — LD matrix from ESSA; INP-020 — samples
58 | Category-Specific Processing | Material Domestic / Import | Material invoice, shipping and LD/Incoterm validation | Implement domestic/import material reconciliation across PO/GRN/invoice and applicable AWB/BL, QC/FAT and LD/Incoterm. | 01-Oct-26 | 14-Oct-26 |  |  |  | Not Started | 0% | BE + DB | INP-008 — 17-incoterm LD matrix from ESSA pending
59 | Category-Specific Processing | Catering / Camp / Housekeeping | Attendance, meal and service reconciliation | Implement reconciliation for catering/camp meal counts and housekeeping service records using biometric/manual registers. | 01-Oct-26 | 14-Oct-26 |  |  |  | Not Started | 0% | BE + DB | INP-018 — Biometric interface; INP-020 — samples
60 | Category-Specific Processing | Travel & Other Non-PO | Travel/HCIS and non-PO service reconciliation | Implement Travel Non-PO/HCIS clearing validation and patterns for consultant, rental, medical, telecom and hotel. | 01-Oct-26 | 14-Oct-26 |  |  |  | Not Started | 0% | BE + DB | INP-020 — samples from ESSA AP team
61 | Category-Specific Processing | Natural Gas | Natural Gas tier/pricing validation | Implement versioned ammonia/benchmark price-tier config, quantity/pricing formula and invoice reconciliation. | 01-Oct-26 | 14-Oct-26 |  |  |  | Not Started | 0% | BE + DB | INP-020 — NG price matrix from ESSA pending
62 | Category-Specific Processing | Composite PO | Composite material/service PO reconciliation | Reconcile material GRN and service SES components; split applicable values; calculate WHT on service portion only. | 01-Oct-26 | 14-Oct-26 |  |  |  | Not Started | 0% | BE + DB | INP-020 — samples from ESSA
63 | Financial Adjustments & Tax | Retention & Advance | Retention and advance-payment recovery calculation/tracking | Calculate applicable retention and advance recovery from approved config/reference values and retain history. | 01-Oct-26 | 12-Oct-26 |  |  |  | Not Started | 0% | BE + DB
64 | Financial Adjustments & Tax | WHT / Treaty | WHT, offshore/treaty and withholding-condition calculation | Implement approved WHT logic including offshore identification, treaty mapping and configurable condition attributes. | 01-Oct-26 | 12-Oct-26 |  |  |  | Not Started | 0% | BE + DB | INP-007 — WHT/treaty mapping from ESSA Tax team
65 | Financial Adjustments & Tax | Faktur Pajak | Faktur Pajak format, age, uniqueness and tax-document validation | Validate Faktur Pajak attributes including format/reference, age/effective-date rules and duplicate/uniqueness controls. | 01-Oct-26 | 12-Oct-26 |  |  |  | Not Started | 0% | BE + DB | INP-019 — Final Faktur Pajak rules from ESSA Tax
66 | Vendor Controls | SAP Negative Vendor | Authoritative SAP Negative Vendor List hard-block | Apply latest synchronized SAP Negative Vendor List snapshot as an inbound hard-block control. | 01-Oct-26 | 14-Oct-26 |  |  |  | Not Started | 0% | BE + DB | INP-009 — SAP objects from ESSA SAP team
67 | Vendor Controls | Vendor Master Controls | Vendor bank-account change/mismatch and EAPA control overlay | Detect vendor bank/account master mismatches and apply independent portal vendor-control/alert overlay. | 01-Oct-26 | 14-Oct-26 |  |  |  | Not Started | 0% | BE + DB
68 | Biometric Integration | Biometric Inbound API | Secured biometric/attendance inbound integration | Expose secured API for approved biometric/attendance payloads, validate schema/source, normalize identities/dates and persist. | 21-Sep-26 | 25-Sep-26 |  |  |  | Not Started | 0% | BE + Integration | INP-018 — Final biometric API payload and security from ESSA IT
69 | Biometric Integration | Availability & Exception Handling | Biometric availability, normalization and manual-verification fallback | Handle delayed/missing/partial biometric data, reconciliation warnings and manual verification without hard-blocking invoices. | 21-Sep-26 | 25-Sep-26 |  |  |  | Not Started | 0% | BE + DB
70 | Workflow & Approval | Workflow Engine | Approval workflow instance, stage and action-state engine | Create workflow instances from published config, manage stages/approvers/action state and prevent conflicting duplicate actions. | 15-Oct-26 | 26-Oct-26 |  |  |  | Not Started | 0% | BE + DB
71 | Workflow & Approval | AP Review | AP Team review, final AP controls and submission to approval | Implement AP review actions/prerequisites, applicable AP Lead control and transition to Approval Pending. | 15-Oct-26 | 26-Oct-26 |  |  |  | Not Started | 0% | FE + BE
72 | Workflow & Approval | DoA & WPC Routing | Delegation of Authority and applicable WPC approval routing | Resolve approver sequence using approved DoA matrix and route WPC-related approval where explicitly in scope. | 15-Oct-26 | 26-Oct-26 |  |  |  | Not Started | 0% | BE + DB | INP-004 — DoA matrix from ESSA Finance
73 | Workflow & Approval | Tax Review | Tax Team review for applicable service invoices | Route applicable invoices through Tax Team review according to agreed sequence and capture decision/remarks. | 15-Oct-26 | 26-Oct-26 |  |  |  | Not Started | 0% | BE + DB | INP-005 — Tax workflow from ESSA Finance/Tax
74 | Workflow & Approval | Microsoft Teams Approval | Teams approve, reject and request-more-info actions | Deliver authenticated approval card/request in Teams and process Approve, Reject and Request More Info actions. | 15-Oct-26 | 26-Oct-26 |  |  |  | Not Started | 0% | BE + Integration | INP-006 — Channel decision from ESSA
75 | Workflow & Approval | Rejection & Resubmission | Rejection, mandatory remarks, return, resubmit and cancellation | Capture mandatory remarks where required and support Rejected→Draft/resubmit and Cancelled paths without losing history. | 15-Oct-26 | 26-Oct-26 |  |  |  | Not Started | 0% | FE + BE + DB
79 | SAP Reference Data Integration | Blob Intake | Azure Blob SAP reference-data file discovery and batch registration | Discover CSV files from SAP ABAP batch to Azure Blob, register source batch/checksum and prevent duplicate ingestion. | 07-Sep-26 | 18-Sep-26 |  |  |  | Not Started | 0% | BE + Integration | INP-010 — CSV contract from ESSA SAP team
80 | SAP Reference Data Integration | CSV Validation & Staging | Inbound CSV schema validation, staging and quarantine | Validate file naming/schema/mandatory columns, stage valid records and quarantine/reject invalid files or rows. | 07-Sep-26 | 18-Sep-26 |  |  |  | Not Started | 0% | BE + DB | INP-009 — SAP objects from ESSA SAP team
81 | SAP Reference Data Integration | Reference Synchronization | PO, vendor, SES and SAP reference synchronization | Upsert approved SAP reference objects into PostgreSQL with source batch/effective timestamps and business keys. | 07-Sep-26 | 18-Sep-26 |  |  |  | Not Started | 0% | BE + DB | INP-009 — SAP objects from ESSA SAP team
82 | SAP Reference Data Integration | Negative Vendor Sync | SAP Negative Vendor List synchronization | Load authoritative SAP Negative Vendor List with batch/effective/source traceability and snapshot history. | 07-Sep-26 | 18-Sep-26 |  |  |  | Not Started | 0% | BE + DB
83 | SAP Reference Data Integration | Inbound Operations | Schedule, reconciliation, archive and replay | Schedule inbound loads, reconcile record/file counts, archive processed files and provide safe replay/recovery controls. | 07-Sep-26 | 18-Sep-26 |  |  |  | Not Started | 0% | BE + DB
84 | SAP Parking / RPA | Parking Queue | EAPA PostgreSQL SAP parking queue | Create durable parking queue with invoice payload, transaction type, state, attempts, idempotency and RPA payload. | 07-Sep-26 | 25-Sep-26 |  |  |  | Not Started | 0% | BE + DB
85 | SAP Parking / RPA | RPA Orchestration | RPA pickup, atomic claim, locking and retry | Implement Power Automate Desktop pickup/claim pattern, lock ownership, attempt history and stale-lock recovery. | 07-Sep-26 | 25-Sep-26 |  |  | Natheera | Not Started | 0% | RPA + Integration | INP-013 — SAP GUI/PAD access from ESSA IT
86 | SAP Parking / RPA | MIRO Parking | PO invoice parking through SAP GUI MIRO | Automate approved MIRO navigation/field mapping for PO invoices and capture SAP response/document reference. | 07-Sep-26 | 25-Sep-26 |  |  | Natheera | Not Started | 0% | RPA + Integration | INP-011 — MIRO field mapping from ESSA SAP; INP-013 — RPA access
87 | SAP Parking / RPA | FB60 Parking | Non-PO invoice parking through SAP GUI FB60 | Automate approved FB60 navigation/field mapping for Non-PO invoices and capture SAP response/document reference. | 07-Sep-26 | 25-Sep-26 |  |  | Natheera | Not Started | 0% | RPA + Integration | INP-011 — FB60 field mapping from ESSA SAP; INP-013 — RPA access
88 | SAP Parking / RPA | GOS Attachments | Invoice/supporting document upload to SAP GOS | Attach approved invoice/supporting documents to correct SAP document through agreed RPA/GOS path. | 07-Sep-26 | 25-Sep-26 |  |  | Natheera | Not Started | 0% | RPA + Integration | INP-012 — GOS requirements from ESSA SAP (Resolved)
89 | SAP Parking / RPA | Parking Result & Recovery | SAP result writeback, lifecycle update and failed-item recovery | Persist SAP document number/result/failure reason, transition eligible invoices to Parked and support retry. | 07-Sep-26 | 25-Sep-26 |  |  | Natheera | Not Started | 0% | BE + DB + RPA
90 | SAP Parking / RPA | Parked Invoice Re-match | Daily GRN/SES re-match and posting-readiness handling | Re-evaluate parked invoices against refreshed GRN/SES/reference data and support path toward posting readiness. | 07-Sep-26 | 25-Sep-26 |  |  |  | Not Started | 0% | BE + DB
91 | SAP Extraction | Status File Creation | Extract invoice/payment status data from SAP | Status file (invoice & payment status) pulled from SAP ABAP batch and made available to EAPA. | 07-Sep-26 | 09-Oct-26 |  |  | ABAP | Not Started | 0% | Integration | INP-010 — CSV contract from ESSA SAP team
92 | SAP Extraction | PO Extraction | Extract Purchase Order data from SAP | PO file (header, item, delivery/billing schedule) pulled from SAP ABAP batch and made available to EAPA. | 07-Sep-26 | 09-Oct-26 |  |  | ABAP | Not Started | 0% | Integration | INP-009 — SAP objects from ESSA SAP team
93 | SAP Extraction | GRN and SES Extraction | Extract Goods Receipt and Service Entry data from SAP | GRN/SES file pulled from SAP ABAP batch and made available to EAPA. | 07-Sep-26 | 09-Oct-26 |  |  | ABAP | Not Started | 0% | Integration | INP-009 — SAP objects from ESSA SAP team
94 | SAP Extraction | Vendor Extraction | Extract Vendor Master data from SAP | Vendor file (master, bank details, blacklist) pulled from SAP ABAP batch and made available to EAPA. | 07-Sep-26 | 09-Oct-26 |  |  | ABAP | Not Started | 0% | Integration | INP-009 — SAP objects from ESSA SAP team
95 | SAP Extraction | SAP IS to Azure Blob | Pass CSV files from SAP Integration Suite to Azure Blob | SAP IS pipeline/channel picks up extracted CSV files and places them into the correct Azure Blob inbound folders. | 14-Sep-26 | 25-Sep-26 |  |  | ESSA | Not Started | 0% | Integration | INP-021 — SAP IS config from ESSA SAP team
96 | SAP Extraction | Azure Blob to AP Platform DB | Load CSV files from Azure Blob into EAPA database | Scheduled ingestion job polls Blob, validates file structure and loads records into EAPA PostgreSQL reference tables. | 14-Sep-26 | 25-Sep-26 |  |  |  | Not Started | 0% | BE + DB
97 | Dashboard & Reporting | Operations Dashboard | AP KPI, workload and operational dashboard | Provide actionable metrics/queues for volumes, lifecycle/stage, pending HITL, approvals, exceptions and SAP processing. | 22-Oct-26 | 02-Nov-26 |  |  |  | Not Started | 0% | FE + BE
98 | Dashboard & Reporting | Invoice Search & Timeline | Invoice search, filters, detail and end-to-end timeline | Search/filter by invoice/vendor/PO/category/status/date and show extraction, validation, workflow and SAP history. | 28-Aug-26 | 04-Sep-26 | 28-Aug-26 |  | Khalid | In Progress | 30% | FE + BE |  | Invoice filtering done. Working on timeline flow and search bar.
99 | Dashboard & Reporting | Operational Views & Exports | Exception/SLA/approval views and CSV/Excel exports | Provide backlog views for exceptions/overdue SLA/pending approvals and configurable CSV/Excel exports. | 22-Oct-26 | 02-Nov-26 |  |  |  | Not Started | 0% | FE + BE
100 | Audit, Logging & Monitoring | Business & Functional Audit | Immutable business/user/config/override/approval/SAP audit trail | Capture lifecycle, document, validation, HITL, config, approval, vendor communication and SAP/RPA events. | 20-Oct-26 | 23-Oct-26 |  |  |  | Not Started | 0% | BE + DB
101 | Audit, Logging & Monitoring | Technical Logging & Diagnostics | Structured logging, correlation IDs and error catalogue | Implement common technical log schema, correlation propagation, severity/event/error codes and redaction. | 20-Oct-26 | 23-Oct-26 |  |  |  | Not Started | 0% | BE
102 | Audit, Logging & Monitoring | Application Monitoring | Application Insights, health, metrics, alerts and support diagnostics | Publish availability, latency, errors, scheduler/integration/GPT/queue health and support-facing diagnostic visibility. | 20-Oct-26 | 23-Oct-26 |  |  |  | Not Started | 0% | BE + Integration
103 | Security & API Controls | API & File Security | API authentication/authorization, request validation and file access controls | Apply auth/authz middleware, input validation, CORS/abuse controls and safe upload/download/doc authorization. | 15-Oct-26 | 26-Oct-26 |  |  |  | Not Started | 0% | BE
104 | Security & API Controls | Secrets & Data Protection | Secrets handling, masking and secure configuration | Keep secrets outside code, enforce approved secret/config references and mask sensitive values in UI/logging. | 15-Oct-26 | 26-Oct-26 |  |  |  | Not Started | 0% | BE
105 | Security & API Controls | Data Integrity & Concurrency | DB integrity, concurrency and immutable-history protections | Implement required FKs/uniqueness/indexes, optimistic/atomic concurrency patterns and append-only audit/history protections. | 15-Oct-26 | 26-Oct-26 |  |  |  | Not Started | 0% | BE + DB
106 | Email Template Config | Admin Email Templates | Email template configuration UI | Configure all email templates: Invoice received, Exception created, Approval requested, Approval overdue, Invoice approved, Invoice rejected, Invoice posted in SAP, Invoice paid, Vendor missing document email. | 28-Aug-26 | 01-Sep-26 | 28-Aug-26 |  | Rahul | In Progress | 5% | FE + BE
107 | Scheduler & Reliability | Scheduler & Recovery Framework | Background schedulers, locking, resilience, retry/replay and runtime controls | Provide reusable scheduling/checkpoint/locking, retry/backoff/circuit/dead-letter patterns and authorized replay/recovery. | 03-Nov-26 | 17-Nov-26 |  |  |  | Not Started | 0% | BE

## ⚠️ Open Inputs (hidden)
ESSA EAPA — Open Inputs & Pending Decisions
These inputs are required from ESSA before the impacted modules can be completed. Update Status as inputs are received.
Input ID | Area | Pending Input / Decision | Impacted Module(s) | Expected From | Status | Remarks
INP-001 | Invoice Categories | Final in-scope invoice category/subcategory list and category codes. | Admin & Configuration; Category-Specific Processing | ESSA AP Team | Open | Required to publish the initial category rollout configuration.
INP-002 | Document Matrix | Final required/optional/conditional supporting-document matrix by category and PO terms. | Admin & Configuration; Core Validation Engine | ESSA AP Team | Open | Required for completeness, conditional-document and processing-mode configuration.
INP-003 | Field Mapping | Final field mapping / Annexure B by document and category. | Admin & Configuration; Azure OpenAI Processing; HITL; Core Validation Engine | ESSA AP Team | Open | Needed for extraction schema, prompts, review and validation context.
INP-004 | DoA Matrix | Complete Delegation of Authority matrix and routing attributes. | Admin & Configuration; Workflow & Approval | ESSA Finance | Open | Required for deterministic approver routing.
INP-005 | Tax Workflow | Final Tax Team applicability and sequence relative to AP/DoA approval. | Workflow & Approval; Financial Adjustments & Tax | ESSA Finance/Tax | Open | Final sequence must be confirmed before workflow completion.
INP-006 | Approval Channels | Final decision on Teams primary, portal fallback and whether direct Email action is supported. | Workflow & Approval; SLA & Notifications | ESSA | Open | Avoid implementing conflicting channel behavior.
INP-007 | WHT / Treaty | Offshore identification, treaty mapping and WHT condition fields. | Financial Adjustments & Tax; Category-Specific Processing | ESSA Tax | Open | Required for deterministic WHT calculations.
INP-008 | LD / Incoterm | Final 17-incoterm LD matrix, milestones and calculation rules. | Category-Specific Processing; Financial Adjustments & Tax | ESSA Procurement/Finance | Open | Required for Material Import and other applicable LD calculations.
INP-009 | SAP Objects | Confirmed SAP reference-data objects, fields and business keys. | SAP Reference Data Integration; Core Validation Engine | ESSA SAP Team | Open | Defines inbound CSV objects and runtime validation context.
INP-010 | SAP CSV Contract | Final CSV naming, schema, schedule and retention/reconciliation rules. | SAP Reference Data Integration; SAP Lifecycle Status Sync | ESSA SAP Team | Open | Required for inbound batch implementation.
INP-011 | SAP Parking Mapping | Final MIRO/FB60 field mapping and parking payload contract. | SAP Parking / RPA | ESSA SAP Team | Open | Required for RPA transaction automation.
INP-012 | SAP GOS | GOS attachment requirements, permissions and supported document behavior. | SAP Parking / RPA | ESSA SAP Team | Resolved | Required for attachment upload automation.
INP-013 | RPA Access | SAP GUI, Power Automate Desktop runtime identity and execution access. | SAP Parking / RPA | ESSA IT / SAP | Open | Required before RPA integration can complete.
INP-014 | Mailbox & SharePoint | Final AP mailbox, service identity, SharePoint intake/storage locations and permissions. | Invoice Ingestion; Document Management | ESSA IT | Open | Required for intake/storage integration setup.
INP-015 | Entra / Fiori | Entra app registration, redirect URLs, groups/role mapping and Fiori launch configuration. | Authentication & Access | ESSA IT | Open | Required for SSO/RBAC and approved launch path.
INP-016 | SLA | Final due-date definitions, reminder/escalation thresholds and calendars. | Admin & Configuration; SLA & Notifications | ESSA AP Team | Open | Required for SLA engine and scheduler.
INP-017 | Error / Retry Policy | Final operational retry limits, replay ownership and recovery boundaries for integrations. | Scheduler, Reliability & Support; Audit, Logging & Monitoring | ESSA IT / Avensys | Open | Can be finalized during detailed design/development.
INP-018 | Biometric Interface | Final biometric/attendance API payload, security, employee mapping and missing-data handling. | Biometric Integration; Category-Specific Processing | ESSA IT / Business | Open | Required for manpower/catering/housekeeping reconciliation.
INP-019 | Faktur Pajak / Tax Rules | Final Faktur Pajak format, age/effective-date, uniqueness and tax validation rules. | Financial Adjustments & Tax | ESSA Tax | Open | Required for deterministic tax-document validation.
INP-020 | Category Samples | Final samples and rule details for Civil, Natural Gas, Catering, Housekeeping, Travel and Composite PO. | Category-Specific Processing | ESSA AP / Tax / Procurement | Open | Used to finalize category-specific algorithms.
INP-021 | SAP IS to Azure Blob | SAP IS pipeline/channel that picks up extracted CSV files and places them in Azure Blob. | SAP Extraction | ESSA SAP Team | Open | SAP IS configuration to maintain file transfer.

## 🗓️ Holidays & Lists (hidden)
Reference Data — Holidays, Statuses, Layers, Resources
SG / PH Holidays | Status | Layer | Resource
10-Aug-26 | Not Started | FE | Rahul
09-Nov-26 | In Progress | BE | Sabrina
25-Dec-26 | Completed | DB | Khalid
01-Jan-27 | Blocked | AI | Natheera
06-Feb-27 | On Hold | RPA | ABAP
07-Feb-27 |  | Integration | ESSA
10-Mar-27 |  | FE + BE | Pranay
26-Mar-27 |  | BE + DB | Anas
|  | FE + BE + DB | Suganth
BE + Integration
BE + AI
RPA + Integration
BE + DB + RPA